## Project Timeline
Privacy Preserving Research Tool - Gantt Chart
Deliverables				May	26	27	28	29	30	31	Jun	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22
Initial Project Background
	Learn TCL and Tk
	Read about various metrices

Coding
	Implement the metrices using the defined formula in TCL
	Implement reading of the file making it ready for calculations
	Implement Uploading of file either by path name or Browse
	Implement a graphical User Interface
Testing
	Reading through books, articles and journals.
	Familiarization of related concepts and terms
Documentation - Draft Report
	Compiling the results together and drafting a report
Presentation
	Preparing for the seminar / presentation
Final Report
	Correcting and drafting the final report